## Sheet1
LIFE
project work plan
| Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb
1: Mapping the landscape | bar: Feb to May
2: Selecting the materials | bar: Jun to Jul
3: Application and analysis | bar: Aug to Jan
4: Evaluation | bar: Nov to Feb
5: Organization of conference | bar: Dec to Feb
Project management